# Assessment 4: Case study: Part B: Conference plan

# Conference plan instructions...

## Scope

Inclusions

- We focus on introducing the difference of our coffee machine from others in the current market.

- Promoting brand awareness to people related in coffee industry in Sydney.

- Boost sales with promotional price.

Exclusions

- Don’t worry about facilities, equipment, and all things needed for conference. The venue will provide them by their own.

- Don’t need to prepare security staff and the cases of emergency patient. The Shangri-la hotel has their own system and staff for them.

- Don’t need to prepare anything for dinner. The hotel will provide dinner buffet for our clients.

#### Reporting

#### Constraints

Cost : upto $25,000

Attendees : upto 60 people (the function hall’s capacity is for 100 pax)

Legislation : a duty of care to the health and safety of your staff, customers and the general public as per the Work Health and Safety Act 2011.

- Health, safety and environment issues include workers' compensation, food handling and safety, safety related to construction sites, ergonomic requirements and security issues.

#### Venue

Location

By foot from the Wynyard Station

#### Program and purpose

| Program | Responsibility | Time (PM) |
| --- | --- | --- |
| Opening speech | Hired comedian | 3:00 – 3:20 |
| Product introduction | Hired comedian/Marketing staff | 3:20 – 4:00 |
| Demonstration how to use good coffee with the machine | World Barista Championship Winner | 4:00 – 4:30 |
| Distribute free sample | Hired staff/Marketing staff | 4:30 – 4:45 |
| Tea break | Hired staff/Marketing staff | 4:45 – 5:30 |
| Question period | Marketing staff | 5:30 – 6:00 |
| Closing speech | Comedian/Marketing boss | 6:00 – 6:20 |
| Dinner time | Hired staff/Hotel staff | 6:20 – 7:20 |

#### Timeline

#### Speakers

Standing comedian who lives around Sydney will be hired. We don’t want him/her to have prevalent knowledge of coffee since we will give him a script to promote our product and will hire a special expert as well. We want a comedian to make conference energetic, and be in good mood. Budget for them is estimated as $10,000 based on 6 times events.

#### Target Audience

The owners and managers of retail coffee shops around Sydney.

#### Budget

| #### Item | #### Description/purpose | #### Cost |
| --- | --- | --- |
| Income | Entry fee | $20,000 |
|  | Sponsors | $10,000 |
| #### Expenses |  |  |
|  | Marketing cost(inc. Advertisement, some events) | $8,000 |
|  | The rental fee for the venue including dinner buffet, facilities, equipment, and all others for the conference | $15,000 |
|  | Hiring a speaker, the winner of the World Barista Championship | $10,000 |
|  | Hiring temporary staff | $2,000 |
|  | Printing brochures/flyers | $600 |
|  | Reserve fund | $6,000 |
| Total expenses |  | $41,600 |
| Surplus/deficit |  | -$11,600 |

#### Risk management

| #### Risk | #### Type | #### Mitigation | #### Contingency | #### Level #### (L,M,H) |
| --- | --- | --- | --- | --- |
| Fire | Hazard | Ask maintenance staff for hotel check the facilities and equipment before rehearsal/Place fire extinguishers around the function hall area. | Post evacuation plans to walls of the function hall/Have staff be well-informed of evacuation plan in advance. | M |
| Cost overrun | Financial | Ensure all future expenses expected and give some extra budget in the stage of budget planning/Strictly keep the record all expenses/All expenses require approval of Marketing Boss | Reserve fund will cover unexpected expenses. If it can’t be covered, the company will | M |
| Low participation rate | Strategic | Promote the conference well to the owners/managers of retail coffee shops around Sydney, Marketing strategy will be organised by marketing staff/Get RSVP and entry fee earlier as soon as possible | Shorten contract-term with the hotel/Reduce entry fee/Turn it into free conference. | H |
| Supply issue | Operational | Check all stocks of tea and etc before rehearsal begin/Check all products’ expired date properly | Store extra stocks in case of high participation rate/Limit the amount of supply which is given to each participant. | M |
| Speaker no show | Operational | There will be high compensation in case of a breach of the contract with a speaker/one or two of our staff will be trained to be alternatives though it is not going to be perfect for our events | One staff will lead a conference in place of a speaker | L |
| Poor service of the venue | Operational | Ensure the quality of service from the venue in the stage of the contract/Ask feedback from participants by each event done/Keep monitoring the service quality/Ask one CS staff from the company | Prepare some free gifts in case of complaints (vouchers/gift card) | M |

#### Promotional strategy

- Distribute flyers including information of the conference and the coffee machine to cafes around Sydney.

- Hold a free coffee distribution event announcing the conference in the crowded street on the city to get attention of people.

- Advertise there is a chance to get free machine for all participants by drawing lots.

- Put an internet advertisement on the well-known coffee website.

Monitoring

- First of all, all plans for the conference require approval of marketing boss before it’s decidedly set up.

- General manager supervises all progress of the preparation and submit a weekly report to the marketing boss

- Marketing manager supervises all progress of the management and the promotion before the event and submit a weekly report to the marketing boss

- General manager keeps his eyes on the expenses record and communicate with the finance department of company to have it on track.

- Hold a meeting fortnightly to discuss the plan and progress before event begins.